PROJECT CHARTER

Patient Satisfaction Analytics: Identifying Key Drivers of Patient Experience

| Project Name | Patient Satisfaction Analytics (HCAHPS) | Prepared By | Mojahed |
| --- | --- | --- | --- |
| Duration | 2 weeks | Date | July 2026 |
| Project Type | Independent portfolio project | Status | Initiation |

# 1. Project Purpose / Business Case

Patient satisfaction is a core indicator of healthcare service quality, yet many hospitals and health systems struggle to identify which specific service dimensions most influence overall patient experience. Without this insight, quality-improvement resources are often spread evenly across departments rather than targeted where they create the most impact.

This project analyzes the U.S. HCAHPS (Hospital Consumer Assessment of Healthcare Providers and Systems) patient satisfaction dataset to identify the key drivers of patient satisfaction and demonstrate how a structured, data-driven analysis can support quality-improvement decisions.

If this analysis is not conducted, quality-improvement teams are left relying on intuition or fragmented survey summaries rather than a consolidated, evidence-based view of what drives patient satisfaction.

# 2. Objectives & Success Criteria

- Identify the top 3–5 service dimensions most strongly associated with overall HCAHPS patient satisfaction scores.

- Build an interactive Power BI dashboard that allows filtering satisfaction results by hospital, region, and service dimension.

- Produce a written summary of findings with at least 3 actionable, evidence-based recommendations for quality improvement.

- Deliver a complete, portfolio-ready project package (charter, analysis, dashboard, final report) within 2 weeks.

# 3. Scope

In Scope:

- Exploratory and descriptive analysis of the HCAHPS dataset.

- Identification of correlations/associations between service dimensions and overall satisfaction.

- Interactive Power BI dashboard for exploring results.

- Final report with executive summary and recommendations.

Out of Scope:

- Advanced predictive modeling / machine learning (descriptive and diagnostic analysis only).

- Comparison with other countries' healthcare systems or datasets.

- Real-time or live data integration (static dataset analysis only).

# 4. Stakeholders

| Stakeholder | Role | Interest |
| --- | --- | --- |
| Mojahed | Project Lead / Analyst | Deliver a complete, high-quality portfolio project demonstrating combined data analytics and project management skills. |
| Prospective employers / reviewers | Portfolio audience | Assess practical, applied competence in analytics and project execution. |
| Healthcare quality-improvement lead (hypothetical) | End user of insights | Would use findings to prioritize quality-improvement initiatives. |

# 5. Milestones / Timeline (2 Weeks)

| Phase | Timing | Milestone |
| --- | --- | --- |
| Initiation | Day 1–2 | Charter finalized; dataset acquired and validated. |
| Data Preparation | Day 3–4 | Data cleaned and structured for analysis. |
| Analysis | Day 5–8 | Exploratory analysis complete; key drivers of satisfaction identified. |
| Dashboard Build | Day 9–11 | Power BI dashboard built and tested. |
| Reporting | Day 11–13 | Findings synthesized into recommendations. |
| Closure | Day 14 | Final report completed; project package assembled for portfolio. |

# 6. High-Level Risks

| Risk | Likelihood/Impact | Mitigation |
| --- | --- | --- |
| Dataset has missing or inconsistent values | Medium / Medium | Budget dedicated data-cleaning time in Day 3–4; document assumptions. |
| Time constraints due to academic workload | Medium / Medium | Fixed 2-week scope with defined out-of-scope items to prevent creep. |
| Dashboard scope creep (adding too many features) | Medium / Low | Lock dashboard requirements before build phase begins. |

# 7. Deliverables

- Project Charter (this document).

- Cleaned dataset and analysis notebook (Python/R).

- Interactive Power BI dashboard (.pbix + published view).

- Final report (PDF): executive summary, methodology, findings, Saudi comparison, recommendations.

- Portfolio summary page (1 page) describing the project for external audiences.

Approved by: Mojahed (Project Lead)          Date: ___________