WORK BREAKDOWN STRUCTURE (WBS)

Patient Satisfaction Analytics (HCAHPS)

# 1. Initiation

| WBS # | Task | Deliverable / Output | Est. Duration | Owner |
| --- | --- | --- | --- | --- |
| 1.1 | Finalize Project Charter | Approved Project Charter | 0.5 day | Mojahed |
| 1.2 | Acquire HCAHPS dataset from official source | Raw dataset file(s) | 0.5 day | Mojahed |
| 1.3 | Validate dataset (columns, size, coverage match expectations) | Data validation notes | 0.5 day | Mojahed |

# 2. Data Preparation

| WBS # | Task | Deliverable / Output | Est. Duration | Owner |
| --- | --- | --- | --- | --- |
| 2.1 | Import & inspect dataset structure | Data dictionary / structure notes | 0.5 day | Mojahed |
| 2.2 | Identify and handle missing values | Cleaned dataset (v1) | 0.5 day | Mojahed |
| 2.3 | Detect and treat outliers/inconsistencies | Cleaned dataset (v2) | 0.5 day | Mojahed |
| 2.4 | Standardize column names, formats, and data types | Analysis-ready dataset | 0.5 day | Mojahed |

# 3. Analysis

| WBS # | Task | Deliverable / Output | Est. Duration | Owner |
| --- | --- | --- | --- | --- |
| 3.1 | Exploratory data analysis (distributions, summary stats) | EDA notebook | 1 day | Mojahed |
| 3.2 | Correlation analysis between service dimensions & overall satisfaction | Correlation results | 1 day | Mojahed |
| 3.3 | Regional / hospital-level comparison analysis | Comparison tables/charts | 1 day | Mojahed |
| 3.4 | Identify top 3–5 key drivers of satisfaction | Key findings summary | 1 day | Mojahed |

# 4. Dashboard Build

| WBS # | Task | Deliverable / Output | Est. Duration | Owner |
| --- | --- | --- | --- | --- |
| 4.1 | Define dashboard requirements (views, filters, KPIs) | Dashboard spec (1-pager) | 0.5 day | Mojahed |
| 4.2 | Load data into Power BI & build data model | Power BI data model | 0.5 day | Mojahed |
| 4.3 | Build visuals (KPI cards, charts, filters/slicers) | Draft dashboard | 1 day | Mojahed |
| 4.4 | Test & refine dashboard (usability, accuracy) | Final dashboard (.pbix) | 0.5 day | Mojahed |

# 5. Reporting

| WBS # | Task | Deliverable / Output | Est. Duration | Owner |
| --- | --- | --- | --- | --- |
| 5.1 | Draft executive summary & key findings | Draft report section | 0.5 day | Mojahed |
| 5.2 | Formulate actionable recommendations | Recommendations section | 0.5 day | Mojahed |
| 5.3 | Compile full report (methodology, findings, visuals) | Draft final report (PDF) | 1 day | Mojahed |

# 6. Closure

| WBS # | Task | Deliverable / Output | Est. Duration | Owner |
| --- | --- | --- | --- | --- |
| 6.1 | Proofread & finalize report | Final report (PDF) | 0.5 day | Mojahed |
| 6.2 | Write 1-page portfolio summary | Portfolio summary page | 0.5 day | Mojahed |
| 6.3 | Assemble & package full project deliverables | Complete portfolio package | 0.5 day | Mojahed |

Note: durations are estimates based on a ~2-week (10 working day) schedule and may overlap slightly (e.g., dashboard build can start before analysis fully concludes).